## Backlog
Task Name | Custom ID | Release | Priority | Size | Depends On | Tags | Description | Acceptance Criteria | BRD Use Cases | Ready
F01 – Staff accounts and secure sign-in | F01 | R1 Foundation | High | M |  | R1,Must,size-M | Value: Every action in the system is done by a known person. Scope: - Individual staff accounts (name, email, role, department) - Sign in / sign out, forgotten password, session timeout - Add, edit and deactivate staff (no deletion of history) - Audit trail of sign-ins and account changes Not in this feature: Charity (partner) accounts → F03; custom roles → F29 Depends on: None BRD use cases: UC01, UC08, UC09 | 1. Given an active staff account, when the user signs in with correct credentials, then their home page opens 2. Given wrong credentials, when the user signs in, then access is refused with a generic message 3. Given a deactivated account, when the user tries to sign in, then access is refused 4. Given any sign-in or account change, then it is recorded with user and time | UC01, UC08, UC09 | Ready
F02 – Role-based workspace | F02 | R1 Foundation | High | M | F01 | R1,Must,size-M | Value: Each person sees only the menus, pages and actions of their role. Scope: - Fixed system roles: Admin, Grants Manager, Reviewer, Committee Secretary, Project Manager, Finance, CEO - Menu and home page per role - Access enforced by the system on every page and action, not only by hiding menus - Departments list for organizing staff Not in this feature: Editable / custom roles → F29 Depends on: F01 BRD use cases: UC02, UC11 Decision needed: Q149 — should system roles be editable? (does not block: fixed roles ship first) | 1. Given a Reviewer, when they open the system, then only their sections appear in the menu 2. Given a user opens a page outside their role by link, then the system blocks it with an access-denied message 3. Given the Admin changes a user's role, then the new access applies at the next action | UC02, UC11 | Needs decision
F03 – Charity self-registration | F03 | R2 Partner registry | High | M | F02 | R2,Must,size-M | Value: Charities register online instead of sending papers. Scope: - Registration with licence number, organization data and delegate details - Delegate mobile / email verification by one-time code - Required documents upload (licence, delegate authorization) - Registration status visible to the applicant Not in this feature: Joining an already registered charity → F05 Depends on: F02 BRD use cases: UC39 Decision needed: Which identity verification is required for delegates (OTP only, or national ID)? | 1. Given a new licence number, when the delegate completes the form and verifies the code, then a registration request is created with status Pending 2. Given a licence number already registered, then the system stops a duplicate registration 3. Given a missing required document, then the request cannot be submitted | UC39 | Needs decision
F04 – Registration review and partner register | F04 | R2 Partner registry | High | M | F03 | R2,Must,size-M | Value: One trusted register of approved charities. Scope: - Queue of registration requests with documents - Approve / return / reject with reason - On approval: charity record and delegate account created - Partner directory with search, filters and Excel export - Add a charity manually and invite its delegate to activate the account Not in this feature: Bank verification and licence updates → F06 Depends on: F03 BRD use cases: UC49, UC50, UC56, UC57 | 1. Given a pending request, when the Grants Manager approves it, then the charity appears in the register and the delegate can sign in 2. Given a request is returned or rejected, then a reason is mandatory and the applicant sees it 3. Given the directory, when the user filters by status, then only matching charities are listed | UC49, UC50, UC56, UC57 | Ready
F05 – Charity portal access and team | F05 | R2 Partner registry | High | M | F04 | R2,Must,size-M | Value: Charities manage their own users without calling the foundation. Scope: - Charity users sign in to the portal; choose the charity if they belong to more than one - Primary delegate adds / deactivates team members (project manager, finance, member) - Transfer of the primary delegation - Join request to an existing charity Depends on: F04 BRD use cases: UC40, UC41, UC55 Decision needed: Can one person belong to more than one charity? (open comment in BRD) | 1. Given a primary delegate, when they add a team member, then that person can sign in to the charity portal 2. Given a non-delegate member, then they cannot add or remove team members 3. Given the delegation is transferred, then the old delegate loses delegate rights immediately | UC40, UC41, UC55 | Needs decision
F06 – Charity profile and verification | F06 | R2 Partner registry | High | M | F05 | R2,Must,size-M | Value: Funding goes only to verified charities and verified bank accounts. Scope: - Charity 360 profile: data, documents, decision history - Confirm or block a charity (with reason) - Bank account (IBAN certificate) verification by staff - Licence / official data update requested by the charity and reviewed by staff Depends on: F05 BRD use cases: UC46, UC51, UC52, UC53, UC54 | 1. Given a charity uploads a new IBAN certificate, then the account stays Unverified until staff verify it 2. Given a blocked charity, then it cannot submit new applications 3. Given any confirm / block / verify decision, then it appears in the charity's history with user and time | UC46, UC51, UC52, UC53, UC54 | Ready
F07 – Annual plan and budget structure | F07 | R3 Plan & opportunities | High | M | F02 | R3,Must,size-M | Value: The annual budget is defined in the system instead of spreadsheets. Scope: - Create the annual plan with total budget - Plan tree: tracks → items → initiatives with budget per level - Edits recorded with an evidence document - Warning when child budgets exceed the parent Not in this feature: Budget adjustments and plan lock → F24; endowments → F25 Depends on: F02 BRD use cases: UC19, UC20, UC21 | 1. Given a new plan, when levels are added, then the tree shows each level's budget and the plan total 2. Given children budgets exceed the parent, then the system warns before saving 3. Given changes are saved, then an evidence document is required and the change is in the plan history | UC19, UC20, UC21 | Ready
F08 – Publish a grant opportunity | F08 | R3 Plan & opportunities | High | M | F07 | R3,Must,size-M | Value: The foundation announces calls for grants in one place. Scope: - Create opportunity: name, description, budget, plan item, open / close dates - Application form from a simple form builder (fields, required flags) - Draft → Published → Closed status - Opportunity list with status and application count Not in this feature: Eligibility targeting and invitations → F10; workflow templates → F28 Depends on: F07 BRD use cases: UC13, UC28, UC29, UC30, UC31 | 1. Given a draft opportunity, then it is not visible to charities until published 2. Given a published opportunity, when the close date passes, then it stops accepting applications 3. Given the opportunity budget exceeds the plan item's available budget, then the system refuses to save | UC13, UC28, UC29, UC30, UC31 | Ready
F09 – Opportunities on the public page and portal | F09 | R3 Plan & opportunities | High | S | F08 | R3,Must,size-S | Value: Charities find open grants without contacting the foundation. Scope: - Public landing page listing published, open opportunities - Portal list of opportunities the charity can apply to - Opportunity details page with dates, budget and conditions Not in this feature: Filtering by eligibility → F10 Depends on: F08 BRD use cases: UC03, UC42 | 1. Given a published opportunity within its dates, then it appears on the public page and in the portal 2. Given a visitor who is not signed in clicks Apply, then they are asked to sign in or register | UC03, UC42 | Ready
F10 – Eligibility, partner groups and invitations | F10 | R3 Plan & opportunities | Normal | M | F09 | R3,Should,size-M | Value: Only the right charities can apply to each opportunity. Scope: - Eligibility rules per opportunity (applicant type, region, groups) - Partner groups for targeting - Private invitations to selected charities - Limit of applications per charity Depends on: F09 BRD use cases: UC32, UC36, UC43, UC58 | 1. Given a charity that does not meet the rules, then the opportunity is not offered to it and it cannot apply 2. Given an invited charity, when it opens the invitation, then it can apply even if the opportunity is private 3. Given the per-charity limit is reached, then a new application is refused | UC32, UC36, UC43, UC58 | Ready
F11 – Submit a grant application | F11 | R4 Applications & decisions | High | M | F09 | R4,Must,size-M | Value: Applications arrive complete and in one place. Scope: - Fill the opportunity's form in the portal, save as draft - Required attachments per opportunity - Requested amount, duration and bill of quantities (items) - Submit with confirmation; application number generated Not in this feature: AI pre-fill → F30 Depends on: F09 BRD use cases: UC44 | 1. Given a missing required field or attachment, then the application cannot be submitted 2. Given a submitted application, then the charity sees it with status Submitted and cannot edit it 3. Given the opportunity is closed, then submission is refused | UC44 | Ready
F12 – My Tasks inbox | F12 | R4 Applications & decisions | High | M | F02 | R4,Must,size-M | Value: Every staff member sees their pending work in one list. Scope: - Inbox with tasks assigned to me, due dates and overdue flags - Manual tasks: create, assign, change status, comment - Meetings with date and attendees - List and calendar views Not in this feature: Bulk decisions and focus mode → F27 Depends on: F02 BRD use cases: UC90, UC91, UC92, UC93 | 1. Given a task is assigned to a user, then it appears in their inbox with its due date 2. Given a task passes its due date, then it is flagged overdue 3. Given a manual task, then only its creator or assignee can change it | UC90, UC91, UC92, UC93 | Ready
F13 – Application review by stages | F13 | R4 Applications & decisions | High | M | F11, F12 | R4,Must,size-M | Value: Applications move through Reception → Study → Approval with clear owners and SLAs. Scope: - Review queue per stage with filters - Application dossier: data, attachments, history - Stage decision: approve to next stage, return for edits, reject (reason required) - Stage tasks created automatically in My Tasks with SLA days Not in this feature: Scoring and pass score → F14; committee minutes → F16; AI evaluation → F30 Depends on: F11, F12 BRD use cases: UC59, UC60, UC62, UC88 Decision needed: Are the three stages fixed, or configurable per opportunity? | 1. Given an application at a stage, then a task is created for that stage's owners 2. Given a reviewer approves, then the application moves to the next stage and the history records who and when 3. Given a rejection, then a reason is mandatory and the charity is notified | UC59, UC60, UC62, UC88 | Needs decision
F14 – Evaluation criteria and pass score | F14 | R4 Applications & decisions | High | S | F13 | R4,Must,size-S | Value: Applications are scored consistently and weak ones cannot be approved by mistake. Scope: - Evaluation criteria with weights per opportunity - Reviewers score each criterion with notes - Pass score: approval blocked below it, wherever the decision is taken Depends on: F13 BRD use cases: UC33 | 1. Given criteria weights that do not total 100%, then they cannot be saved 2. Given the total score is below the pass score, then approval is blocked 3. Given a scored application, then the dossier shows each reviewer's score and notes | UC33 | Ready
F15 – Charity follow-up and requested edits | F15 | R4 Applications & decisions | High | M | F13 | R4,Must,size-M | Value: Charities see where their application is and respond quickly. Scope: - Application status and expected reply date in the portal - Returned for edits: charity edits the data / attachments and resubmits - Staff-proposed changes to amounts or quantities accepted or refused by the charity Depends on: F13 BRD use cases: UC45, UC63 | 1. Given an application is returned for edits, then the charity can change its data and resubmit to the same stage 2. Given staff propose a new amount, then it applies only after the charity accepts it 3. Given a final decision, then the charity sees the decision and reason | UC45, UC63 | Ready
F16 – Committee decisions by minute | F16 | R4 Applications & decisions | High | M | F14 | R4,Must,size-M | Value: Committee decisions are recorded once and applied to all the applications they cover. Scope: - Committee secretary selects applications at the Approval stage - Minute with date, members, decision per application and the signed minute file - Decisions applied to all selected applications in one step Depends on: F14 BRD use cases: UC64, UC95 | 1. Given a minute is saved with decisions, then each application moves according to its decision 2. Given a minute without the signed file, then it cannot be finalized 3. Given an application decided by minute, then its history links to the minute | UC64, UC95 | Ready
F17 – Contract and project from an approved application | F17 | R5 Contracts & projects | High | M | F16 | R5,Must,size-M | Value: Approved grants become signed contracts and trackable projects without retyping. Scope: - Contract generated from the application (parties, amount, items, payment schedule) - Payment schedule as % of amount per milestone - Contract signing status - Project created with budget and project manager Not in this feature: Splitting one application into several projects → F30C Depends on: F16 BRD use cases: UC67, UC69, UC70, UC71 | 1. Given an approved application, when the Grants Manager transfers it, then one contract and one project are created with the approved amount 2. Given the payment schedule does not total 100%, then the transfer is refused 3. Given a contract is not signed, then project execution cannot start | UC67, UC69, UC70, UC71 | Ready
F18 – Project plan and start of execution | F18 | R5 Contracts & projects | High | M | F17 | R5,Must,size-M | Value: Each project has an agreed plan before work starts. Scope: - Project plan: milestones, activities, due dates, linked payments - Start execution (requires signed contract and complete plan) - Project portfolio list with status and overdue (stalled) flag Not in this feature: Plan changes after start → F20 Depends on: F17 BRD use cases: UC72, UC74 | 1. Given a signed contract and a complete plan, when the project manager starts execution, then the project status becomes In progress 2. Given an activity passes its due date without approval, then the project is flagged stalled | UC72, UC74 | Ready
F19 – Charity progress reports and milestone approval | F19 | R5 Contracts & projects | High | M | F18 | R5,Must,size-M | Value: Progress is proven with evidence before money is released. Scope: - Charity submits task progress, evidence files and milestone reports in the portal - Project manager verifies evidence: accept or return with note - Milestone approved → its payment becomes due Not in this feature: Indicators → F30C Depends on: F18 BRD use cases: UC47, UC75, UC76 | 1. Given a charity submits a milestone report with evidence, then the project manager gets a task to verify it 2. Given evidence is returned, then the charity sees the note and can resubmit 3. Given a milestone is approved, then its linked payment becomes Due | UC47, UC75, UC76 | Ready
F20 – Plan revisions and project closure | F20 | R5 Contracts & projects | Normal | M | F19 | R5,Should,size-M | Value: Changes and closure are controlled and documented. Scope: - Request a plan revision with reason; approved by a different person - Close the project after all milestones are approved, with a final evaluation Depends on: F19 BRD use cases: UC77, UC78 | 1. Given a revision request, then the requester cannot approve it 2. Given unapproved milestones, then the project cannot be closed 3. Given a project is closed, then no new tasks or payments can be added | UC77, UC78 | Ready
F21 – Payment approval chain | F21 | R6 Payments | High | M | F19 | R6,Must,size-M | Value: No payment is released without the required approvals. Scope: - Due payments list per project - Submit a due payment for approval - Three-level approval: project manager → Grants Manager → CEO; reject with reason returns it to Due - Approval tasks created in My Tasks Depends on: F19 BRD use cases: UC80, UC81, UC89 Decision needed: Are there amount thresholds that change the approval chain? | 1. Given a due payment is submitted, then the project's manager gets an approval task 2. Given step 1 is approved, then the Grants Manager gets the next task; after step 2 the CEO 3. Given any rejection, then a reason is mandatory and the payment returns to Due 4. Given a person approved one step, then they cannot approve another step of the same payment | UC80, UC81, UC89 | Needs decision
F22 – Disbursement order, transfer and receipt | F22 | R6 Payments | High | M | F21, F06 | R6,Must,size-M | Value: Finance pays the right account and every payment is closed with proof. Scope: - Disbursement order issued after final approval - Payee confirmed (charity's verified bank account; third party only with re-approval) - Finance records the bank transfer and uploads the transfer notice - Charity uploads the receipt voucher; payment closed as Paid Depends on: F21, F06 BRD use cases: UC82, UC83, UC84 | 1. Given a payment is fully approved, then a disbursement order is issued with a unique number 2. Given the bank account is not verified, then the transfer cannot be recorded 3. Given the payee is changed after approval, then the approval chain restarts 4. Given the receipt voucher is uploaded, then the payment status becomes Paid | UC82, UC83, UC84 | Ready
F23 – Payments register and commitments | F23 | R6 Payments | High | S | F22 | R6,Must,size-S | Value: Finance and management see every payment and what is still owed. Scope: - Payments register with status, partner, project and amounts - Commitments per charity (scheduled vs paid) - Excel export Depends on: F22 BRD use cases: UC79, UC85 Decision needed: Single definition of “paid” (after transfer or after receipt?) | 1. Given the register, then each payment shows its current status and who it waits for 2. Given a charity, then its committed, due and paid totals add up to its contracts' amounts | UC79, UC85 | Needs decision
F24 – Budget monitoring and adjustments | F24 | R7 Insight & efficiency | High | M | F23 | R7,Must,size-M | Value: The foundation always knows used, committed, paid and available budget. Scope: - Live budget figures per plan level: committed, due, paid, available - Budget increase / decrease / transfer with evidence document - Financial operations register and plan history - Lock and reopen the plan Depends on: F23 BRD use cases: UC22, UC23, UC24, UC25 | 1. Given a contract is signed, then the plan item's committed amount increases by the contract amount 2. Given a decrease larger than the available amount, then it is refused 3. Given any adjustment, then an evidence document is required and the operation is in the register | UC22, UC23, UC24, UC25 | Ready
F25 – Endowments | F25 | R7 Insight & efficiency | Normal | M | F24 | R7,Should,size-M | Value: Each endowment's share of the plan and its use are visible. Scope: - Register endowments (funding sources) - Record endowment funding - Endowment share per plan level and endowment report Depends on: F24 BRD use cases: UC16, UC26, UC27 Decision needed: How are endowment shares decided (equal, by size, manual)? | 1. Given endowments participate in a plan item, then the item's budget is split by their shares 2. Given an endowment is used in a plan, then it cannot be deleted | UC16, UC26, UC27 | Needs decision
F26 – Executive dashboard and reports | F26 | R7 Insight & efficiency | Normal | M | F23 | R7,Should,size-M | Value: Management gets the numbers without asking the team. Scope: - Dashboard: budget, applications by stage, projects, payments, delays - Standard reports (applications, projects, payments, partners) with filters and Excel export - Staff workload and performance view Depends on: F23 BRD use cases: UC12, UC86, UC87 Decision needed: Which reports does management request today? | 1. Given the dashboard, then figures match the registers they come from 2. Given a report with filters, when exported, then the Excel file contains the same rows | UC12, UC86, UC87 | Needs decision
F27 – Productivity tools | F27 | R7 Insight & efficiency | Low | M | F13, F21 | R7,Could,size-M | Value: Staff spend less time navigating and deciding. Scope: - Global search across partners, applications, projects and payments - Saved views and list exports - Decide directly from a task, and bulk decisions - Focus mode for processing tasks one by one Depends on: F13, F21 BRD use cases: UC04, UC06, UC07, UC94, UC96 | 1. Given a search term, then results show only records the user may access 2. Given a decision from a task or focus mode, then the same rules apply as on the application page (e.g. pass score) | UC04, UC06, UC07, UC94, UC96 | Ready
F28 – Configuration library and governance | F28 | R8 Advanced grant types & AI | Low | M | F13 | R8,Could,size-M | Value: Admins reuse setups and every sensitive change is traceable. Scope: - Workflow templates reusable across opportunities - Communication templates and reference lists - Applicant types open / closed for registration - Sensitive configuration changes require an evidence document and keep history Depends on: F13 BRD use cases: UC14, UC15, UC18, UC34, UC38 | 1. Given a template is applied to an opportunity, then its stages and criteria are copied 2. Given a sensitive setting is changed, then an evidence document is required and the old value is kept in history | UC14, UC15, UC18, UC34, UC38 | Ready
F29 – Custom roles and permissions | F29 | R8 Advanced grant types & AI | Normal | M | F02 | R8,Should,size-M | Value: The foundation adapts access to its own structure. Scope: - Permission matrix (view / write / delete) by role - Create custom roles, optionally copying a system role - Enable / disable permissions for a whole role, with change history Depends on: F02 BRD use cases: UC10 Decision needed: Q149 — may system roles be edited, or only custom roles? | 1. Given a permission is disabled for a role, then every user with that role loses it at their next action 2. Given a custom role is assigned to staff, then it cannot be deleted 3. Given any permission change, then it is recorded with user, time and before / after | UC10 | Needs decision
F30 – AI assistance | F30 | R8 Advanced grant types & AI | Low | M | F13 | R8,Could,size-M | Value: AI saves time on forms and evaluation while people keep every decision. Scope: - AI pre-fill of application forms from uploaded documents (charity confirms) - AI document check on attachments (advisory) - AI evaluation summary for reviewers and external AI evaluation report - AI assistant for questions on grant data (read-only, proposes links) Depends on: F13 BRD use cases: UC05, UC48, UC61 Decision needed: Which AI provider, and what data may be sent to it? | 1. Given AI proposes values, then nothing is saved until the user confirms 2. Given an AI check flags a document, then the user can still proceed (advisory only) 3. Given the AI assistant answers, then it uses only data the user may access | UC05, UC48, UC61 | Needs decision
F31 – In-kind (product) grants | F31 | R8 Advanced grant types & AI | Low | M | F14 | R8,Could,size-M | Value: The foundation can grant products from its stock, not only money. Scope: - Product catalog with stock - Product opportunities and product requests - Approval deducts stock; delivery recorded Depends on: F14 BRD use cases: UC35, UC68 | 1. Given a request above available stock, then it is refused 2. Given a product grant is approved, then stock is deducted once and delivery is tracked | UC35, UC68 | Ready
F32 – Tendered projects (RFP) | F32 | R8 Advanced grant types & AI | Low | M | F17 | R8,Could,size-M | Value: The foundation can tender a defined project and award the best offer. Scope: - Define the tendered project (scope, deliverables, budget) - Invited charities submit offers; side-by-side comparison - Award to one evaluated offer; others closed with notice; contract and project created Depends on: F17 BRD use cases: UC37 | 1. Given an offer above the budget, then it is refused 2. Given an RFP is awarded, then only an evaluated offer above the pass score can win 3. Given an award, then all other offers are closed and notified | UC37 | Ready
F33 – Multi-project grants, merges and funding conditions | F33 | R8 Advanced grant types & AI | Low | M | F17 | R8,Could,size-M | Value: Complex grants are handled without workarounds. Scope: - Split one application into several projects - Merge applications of the same charity - Funding conditions, co-funding and indicators - Internal initiatives run by the foundation Depends on: F17 BRD use cases: UC65, UC66, UC73 | 1. Given an application is split, then the projects' budgets total the approved amount 2. Given co-funding conditions are unconfirmed, then final approval is blocked 3. Given merged applications, then one contract is created | UC65, UC66, UC73 | Ready
F34 – Multi-organization platform | F34 | R8 Advanced grant types & AI | Low | M | F02 | R8,Won't (this year),size-M | Value: Several grantor foundations can use the same platform separately. Scope: - Platform admin registers and suspends grantor organizations - Strict data isolation between organizations Depends on: F02 BRD use cases: UC17 Decision needed: Is Manih for one foundation or several? | 1. Given two organizations, then users of one never see the other's data 2. Given an organization is suspended, then its users cannot sign in | UC17 | Needs decision